{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Tabelle1","Tabelle2","Tabelle3"],"not_rendered":{"external_links":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Tabelle1","index":0,"n_rows":30,"n_cols":4,"rows_kept":30,"flags":["formulas_cached_only"]}
["KW","Datum","Phase","Tätigkeit"]
[36,"2011-08-29","Prototyp Ecartec","Grobentwurf Gesamtsystem, Inbetriebnahme Hardware, Entwicklungsumgebung X2E,\nFestlegung Funktionsumfang Ecartec-Prototyp"]
[37,"2011-09-05","Prototyp Ecartec","Spezifikation API, Protokoll"]
[38,"2011-09-12","Prototyp Ecartec","Spezifikation Connector, Executor, Adaptor"]
[39,"2011-09-19","Prototyp Ecartec","Implementierung Prototyp Connector, Adaptor"]
[40,"2011-09-26","Prototyp Ecartec","Implementierung Prototyp Recorder, Executor"]
[41,"2011-10-03","Prototyp Ecartec","Implementierung Prototyp Log-Plugin"]
[42,"2011-10-10","Prototyp Ecartec","Implementierung CanEasy-Anbindung"]
[43,"2011-10-17","Prototyp Ecartec","Integration, Test Ecartec-Prototyp"]
[43,"2011-10-18",null,"Ecartec"]
[43,"2011-10-19",null,"Ecartec"]
[43,"2011-10-20",null,"Ecartec"]
[44,"2011-10-24","Erweiterte Funktionen","Dokumentation der bisherigen Ergebnisse"]
[45,"2011-10-31","Erweiterte Funktionen","Dokumentation der bisherigen Ergebnisse\nLiteraturrecherche, 1. Version zum Review"]
[46,"2011-11-07","Erweiterte Funktionen","Implementierung Erweiterung Connector, Adaptor"]
[47,"2011-11-14","Erweiterte Funktionen","Implementierung Erweiterung Connector, Adaptor"]
[48,"2011-11-21","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[49,"2011-11-28","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[50,"2011-12-05","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[51,"2011-12-12","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[52,"2011-12-19","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[53,"2011-12-26","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[1,"2012-01-02","Erweiterte Funktionen","Implementierung Erweiterung Executor, Plugin-Generator"]
[2,"2012-01-09","Erweiterte Funktionen","Schreiben"]
[3,"2012-01-16","Erweiterte Funktionen","Schreiben"]
[4,"2012-01-23","Erweiterte Funktionen","Schreiben"]
[5,"2012-01-30","Erweiterte Funktionen","Schreiben"]
[6,"2012-02-06","Erweiterte Funktionen","Korrektur, Drucken, Binden"]
[7,"2012-02-13"]
[7,"2012-02-14",null,"Abgabe"]

{"sheet":"Tabelle2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Tabelle3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}